Minutes of 4th EDWIN project meeting, Mannheim, June 23, 2004.

Administrative matters:

- Partners were reminded to send in background material for the 3rd progress report (1.11.2003 – 30.4.2004), which should be delivered to the Commission no later than end of June, 2004.

- The coordinator contacts the scientific contact person of the project to consult him about the problems caused to the project by the delay in getting access to the ECHP 1994-2001 data. (done)

- The next project meeting will be held in Madeira in October 3-4, 2004. The meeting will focus on partner presentations of both cross-country and country-specific research (please also check the Technical Annex to remind yourselves about what we have promised to do). Each presentation will be assigned a commentator. Written material should therefore be made available at least two weeks before the meeting. The Portuguese team has promised to take care of practical matters such as hotel booking.

Deliverables:

- The literature review has been further delayed because of missing contributions from partners. According to the current time table, the book will appear in ETLA’s series in late August.

- The second (and final) policy-oriented workshop will be held in Brussels in late April, 2005. The programme will consist of comprehensive policy-oriented papers reviewing the current state of knowledge, the main contributions of EDWIN, and a discussion of policy implications. The preliminary programme contains contributions by Panos (overall wage inequality), Claudio (cohort effects, including Charlotte’s and Giorgio’s findings), Pedro (within-group inequality), Erling (LM institutions), Ali (gender), Peter (over-education), Charlotte (quality), Giorgio (or Rita on training), with the emphasis on WP5 topics. The given names refer to the person in charge, who is, of course, free to engage other partners/researchers in their contribution.

- It was decided that EDWIN takes as its goal to offer a manuscript to an international publisher based on the cross-country papers presented at the Brussels workshop. This book project (~ introduction + 8 chapters) will be discussed in more detail at the Madeira meeting.

Workpackages:

- Panos, Claudio, Charlotte, Pedro and Peter gave a brief review of what they intended to present at the workshop the next day.

- The discussion of the country-specific results clearly showed that each partner needs to check carefully the results and findings of his/her country. In other words, each partner’s responsibility does not stop with the delivery of the data and results asked for. These checks should be made over the next few months, preferably before the end of August, so that the responsible partners can finalise workpackages 2, 3 and 4 well before the Madeira workshop.

- WP5, over-education: the Swedish team will approach partners with an inquiry (different from the previous one) in an attempt to explore the possibilities to undertake an analysis of over-education based on national data.

- WP5, gender: Ali reported that a comprehensive French study has been undertaken. The inquiry to partners concerning available national data revealed that few partners can meet the data requirements to be able to repeat the French study. The team responsible for the gender issue will, therefore, rely on ECHP data in the next stage of their research.

- An up-dated version of the WP5 responsibility table can be found on the next page.

| WP5 tasks: | Summary paper on WPs 2 – 4 | LM institutions & flex | Over-education | Quality | Gender | Training |
| --- | --- | --- | --- | --- | --- | --- |
| # Finland | ## Responsible |  |  | Contributes with paper on Finland |  | co-ordinator Literature review + Finnish paper |
| Greece |  | principal collaborator |  |  | Greek paper + cross-country paper based on the ECHP (by Yiannis) |  |
| Italy |  | principal collaborator |  |  | Italian paper (by Simona) | Two papers by Giorgio based on ECHP data. |
| Portugal |  |  |  |  |  | 2 Portuguese papers |
| France |  |  |  | Contributes with paper on France | co-ordinator |  |
| Norway | Responsible | co-ordinator (+ 2 papers on Norway) |  | Contributes with paper on Norway |  |  |
| Sweden |  |  | co-ordinator (+ Swedish paper) | Contributes with paper on sec. school level quality differences | Swedish paper (by Calle) | Swedish paper (by Calle) |
| UK |  |  | principal collaborator (+ one UK paper) | Contribute with at least two papers on the UK | co-ordinator | Cross-country training paper by Peter. |
| Germany |  |  |  | Contributes with PISA study paper |  |  |